## Action & Issue Register
Travel Policy Update Project - Actions & Issues |  |  | Last Updated: 6/9/15 |  |  | Press CTRL + S to sort by Priority (High,Med,Low) and Est Compl Date. Press CTRL + D to update the "Last Updated" date.
Action# | Priority | Description | Owner | Originator | Open Date | Next Update Date | Status | Close Date | Status, Actions, or Resolutions (include mm/dd/yy)
4 | Low | Finish Kickoff Presentation and schedule the kickoff meeting | Adam | Sally | 2015-05-25 | 2015-05-30 | Closed | 2015-05-30 | 5/25 - Project has been authorized. Adam is PM. He will coordinate the kickoff meeting.
5 | Med | Contact Rental Car vendor re: Insurance. Get Rental Car vendor contact info from John | Bill | Sally | 2015-06-01 | 2015-06-04 | Open |  | 6/1 - Need to contact Rental Car vendor to verify insurance information. Bill will get info from John and then call vendor by 6/4.
6 | Med | Gather language for "preferred choice" airline provider for international flight section of policy | Dave | Dave | 2015-06-01 | 2012-06-09 | Open |  | 6/7 - Sally has deligated the language to Jeff D. Dave to contact Jeff. 6/1 - Dave will revise the "preferred choice" language. He is going to meet with Procurement Exec Dir to discuss and gather language.
7 | High | Coordinate schedules for the policy approval meetings | Adam | Sally | 2015-06-01 | 2012-06-12 | Open |  | 6/1 - Sally is on vacation, so schedule coordination may be difficult. Need to do it now to secure the date.
8 | Med | Notify Compliance that we will be requesting approvals after 6/21. Need to get process started. | Adam | Adam | 2015-06-07 | 2012-06-14 | Open
9 | Med | Onboard the new Procurement Manager on the project. | Sally | Adam | 2015-06-09 | 2015-06-16 | Open
Note on B2: Low = No impact to deliverables or schedule Med = Possible impact to deliverables or schedule High = If no action taken, will impact deliverables or schedule

## Scope-Objectives
Scope Statement
This project will serve to update the university's travel and expense policies in time to make them effective at the beginning of the calendar year. Project excludes updates to P-Card Policy which will be handled under a separate project.
Stated Objectives of the Initiative
Analyze, recommend and implement approved changes for the following policies: - Travel Policy (Car Rental, Hotel, Airfare) - Entertainment Policy (Meals, Entertainment, Alcohol) - Travel Insurance
Have updated policies approved and published by start of calendar year
Develop a communication plan to educate stakeholders on policy updates

## Stakeholder Matrix
Name | Title | Department / Group | Category | Contact | Impact (H/M/L) | Influence (H/M/L)
Adam Donaldson | Manager | Business Management & Analysis Group | Project Team | 202-994-6867 adonald@gwu.edu | H | M
Sally Doe | Executive Director | Procurement | Project Owner | 703-555-1212 sally_doe@gwu.edu | M | M
John Doe | Travel Manager | Procurement | Subject Matter Expert | 202-555-1212 john_doe@gwu.edu | H | M
Jane Doe | Compliance Manager | Compliance | Subject Matter Expert | 202-555-1213 jane_doe@gwu.edu | H | L
Bill Doe | Director | School Budget Officers | Stakeholder | 202-555-1214 bill_doe@gwu.edu | M | L
Note on F1: Direct interaction with the project / will likely affect the day to day activities.
Note on G1: Extent to which they are able to persuade others into following certain courses of action

## Requirements List
# | Requirement Name / Description | Category | Sub Category | Benefit | Priority Categorization
1 | Travel policy updates shall specify preferred rental car vendors | Travel Policy | Rental Car | Allows policy readers to know the preferred vendors. However, it is also on the website, so not a "must have". | Should Have
2 | Travel policy update shall clarify rental car insurance policies | Travel Policy | Rental Car | Ensures travelers understand when they are supposed to self-insure with the rental care company. | Must Have
3 | Travel policy shall revise and clarify business class travel rules for international flights | Travel Policy | Air | Reduce unallowed use of business class in order to reduce travel expenses. | Must Have
4 | Entertainment policy shall include a per diem and clarify amounts | Entertainment Policy | Per Diem | Per Diem is not included in current travel policy. So this will be new and must be clarified. | Must Have
5 | Entertainment policy shall specify exlusions to company-paid expenses. | Entertainment Policy | Per Diem | Exclusions aren't required for the policy, but will help clarify allowable expenses. | Should Have
6 | Travel Policy should include after hours contact information. | Travel Policy | General | Contact info could be included in the policy. However, because it may change over time, we may want to simply refer to website. | Nice To Have

## WBS
Partial Example

## Schedule
ID | Task | Start | Finish | Deadline | Work | Duration | % Cmpl | Predecessors | Resource
| Rental Car Policy Updates | 2012-06-03 | 2012-06-05 | - | 30 hrs | 14 days | 7%
1 | Gather Stakeholder Feedback | 2015-06-03 | 2015-06-07 | - | 8 hrs | 5 days | 20% |  | John Doe
2 | Update Preferred Vendor Information | 2015-06-10 | 2015-06-14 | - | 16 hrs | 5 days | 0% | 1 | John Doe
3 | Update Rental Car Insurance Instructions / Policy | 2015-06-17 | 2015-06-18 | - | 2 hrs | 2 days | 0% | 2 | Sally Doe
4 | Dept Approval of Rental Car Section | 2015-06-19 | 2015-06-20 | - | 4 hrs | 2 days | 0% | 3 | Sally Doe
5 | Rental Car Section Updated Ready for Approval Process | 2015-06-21 | 2015-06-21 | 2015-06-21 | - | - | 0% | 4
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21

## Communication Matrix
# | Communication | Medium | Delivery Date | Frequency | Description/Notes | Audience | Reviewer | Owner | Status
1 | Project Kickoff w/ Stakeholders | Meeting | 2015-06-01 | Weekly | In draft form … pending first review | Finance Directors Department Heads | N/A | Adam Donaldson | Open
2 | Notification of Policy Update Efforts | Email | 2015-06-15 | One Time |  | Faculty & Staff via Infomail | Jane Doe | John Doe | Open
3 | Focus Groups for Update Gathering | Meeting | 2015-06-22 | One Time | Discuss proposed changes to web content, including development efforts | Finance Directors / Departments | N/A | John Doe | Open
4 | Notification of New Policy When Effetive | Email | 2015-07-01 | One Time | 2 hrs | Finance | N/A | John Doe | Open
5 | Status Report | Memo | 1-Jun through 1 Jul | Weekly | Weekly status report showing progress, issues, and timeline | Executive VP & Treasurer | Jane Doe | Adam Donaldson | Open

## Lessons Learned
Observation | Originator | Impacted Groups | Phase | Recommended Future Course of Action
Status reporting format and frequency was very well received. Senior management recommended we use this format for other similar initiatives. | SAVP Finance | BMAG Department | All | Distribute this status reporting format to other teams for use on similar initiatives.
Development of the requirements didn't originally include any discussion with External Relations … so we initial missed several of the graphic development requirements. These were added later with some minor disruption to the project. | Project Team | BMAG Department, External Relations | Define | During stakeholder matrix development, think more broad when considering those impacted by the project.
Departmental employees were solicited too late in the project to provide content. This led many employees to ignore our requests | Project Team | BMAG Department | Planning / Manage | Communicate much earlier in the process to those from whom we wish to solicit content for the next upgrade.